## Product Backlog
Product backlog
| ID | Description | Priority | Size
| PBI-5 | All ideas can be categorised (tagged) from a list of categories at the point when they are submitted | must | 0.5
| PBI-2 | All staff (academic and support) have the opportunity to submit one or more ideas | must | 20
| PBI-3 | All staff must agree to Terms and Conditions before they can submit | must | 2
| PBI-13 | Lists of Ideas need to be paginated | must | 0.5
| PBI-1 | All Departments have a QA coordinator who is responsible for managing the process for their Department, and for encouraging staff to contribute. | must | 1
| PBI-15 | An administrator is needed to maintain any system data, e.g. closure dates for each academic year, staff details | must | 8
| PBI-14 | The University QA Manager needs to be able to download all the data after the final closure date in a CSV file for transfer out of the system. Any uploaded documents need to be downloaded in a ZIP file | should | 20
| PBI-4 | All staff can optionally upload documents to support their ideas | should | 8
| PBI-7 | All staff can see all submitted ideas and can comment on any idea. They can also give the Thumbs Up or Thumbs Down for any idea, but only once for any idea | should | 2
| PBI-10 | Once an idea is submitted the system emails a notification to the Department’s QA Coordinator | could | 5
| PBI-17 | The interface must be suitable for all devices | could | 13
| PBI-12 | Lists of Most Popular Ideas (+1 for Thumbs Up, -1 for Thumbs Down), Most Viewed Ideas, Latest Ideas and Latest Comments must be made available to all users | could | 1
| PBI-16 | Statistical analysis (e.g. number of ideas per Department) needs to be available | could | 20
| PBI-9 | All new ideas are disabled after a closure date for new ideas, but comments can continue to be done until a final closure date | could | 2
| PBI-8 | Ideas and comments can be posted anonymously, although the author’s details will be stored in the database so any inappropriate ideas can be investigated | could | 8
| PBI-11 | The author of an idea receives an automatic email notification whenever a comment is submitted to any of their ideas | could | 5
| PBI-6 | The QA Manager can add additional categories at any time, and can delete categories, but only if they have not been used | could | 1

## Đừng đọc cái này
Sprint 1: Feb 22th - Feb 28th 2022 Sprint goal: Function Register / Login / User Role
From product backlog name : All staff must agree to Terms and Conditions before they can submit.
Task ID | Task Name | Sprint Task | Name | Estimate time (hours) | Working date | Status 1 | Actual time (hours) | Finishing date | Status 2
1 | Structure Design | Design ERD, database | Tung, Hoang Huy | 20 | Feb 22nd - Feb 24th | Working in progress | 16 | Feb 25nd | Done
2 | Back-End Implement | Create user account | Tung, Hoang Huy, Ngọc Thien, Quang Huy | 20 | Feb 22th - Feb 28th | Working in progress | 25 | Feb 28th | Done
3 | Front-End Implement | Design Register Page | Quang Huy, Dinh Hieu | 8 | Feb 25th - Feb 27th | Working in progress | 12 | Feb 26th | Done
4 |  | Design Login Page | Quang Huy, Dinh Hieu | 8 | Feb 24th - Feb 27th | Working in progress | 10 | Feb 27th | Done
5 | Testing | Test completed function | Hieu | 5 | Feb 28th | Working in progress | 9 | Feb 28th | Done
6 | Total | Total |  | 61 |  |  | 72
|  | Initial Estimate (hour) | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday
| TaskID | Day 0 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | Feb-26th | Feb 27th | Feb 28th | Mar 1st | Mar 2nd | Mar 3th
| 1 | 20 | 4 | 4 | 4 | 4
| 2 | 20 | 4 | 4 | 3 | 3 | 4 | 4 | 3
| 3 | 8 |  | 4 | 3 | 3 | 2
| 4 | 8 |  |  | 3 | 3 | 3 | 1
| 5 | 5 |  |  |  |  | 3 | 3 | 3
| Remaining Effort | 61 | 53 | 41 | 28 | 15 | 3
| Idea line | 61 | 54.9 | 48.8 | 42.7 | 36.6 | 30.5 | 24.4 | 18.3 | 12.2 | 6.1 | 0

## Release Planing
ID | Description | Priority | Size | Points
PBI-2 | All staff (academic and support) have the opportunity to submit one or more ideas | must | 20 | 31
PBI-5 | All ideas can be categorised (tagged) from a list of categories at the point when they are submitted | must | 0.5
PBI-13 | Lists of Ideas need to be paginated | must | 0.5
PBI-3 | All staff must agree to Terms and Conditions before they can submit | must | 2
PBI-15 | An administrator is needed to maintain any system data, e.g. closure dates for each academic year, staff details | must | 8
PBI-14 | The University QA Manager needs to be able to download all the data after the final closure date in a CSV file for transfer out of the system. Any uploaded documents need to be downloaded in a ZIP file | should | 20
PBI-4 | All staff can optionally upload documents to support their ideas | should | 8 | 34
PBI-7 | All staff can see all submitted ideas and can comment on any idea. They can also give the Thumbs Up or Thumbs Down for any idea, but only once for any idea | should | 2
PBI-1 | All Departments have a QA coordinator who is responsible for managing the process for their Department, and for encouraging staff to contribute. | should | 1
PBI-9 | All new ideas are disabled after a closure date for new ideas, but comments can continue to be done until a final closure date | should | 2 | 39
PBI-6 | The QA Manager can add additional categories at any time, and can delete categories, but only if they have not been used | should | 1
PBI-10 | Once an idea is submitted the system emails a notification to the Department’s QA Coordinator | could | 5
PBI-17 | The interface must be suitable for all devices | could | 13
PBI-12 | Lists of Most Popular Ideas (+1 for Thumbs Up, -1 for Thumbs Down), Most Viewed Ideas, Latest Ideas and Latest Comments must be made available to all users | could | 1 | 13
PBI-16 | Statistical analysis (e.g. number of ideas per Department) needs to be available | could | 20
PBI-8 | Ideas and comments can be posted anonymously, although the author’s details will be stored in the database so any inappropriate ideas can be investigated | could | 8
PBI-11 | The author of an idea receives an automatic email notification whenever a comment is submitted to any of their ideas | could | 5

## Srpint Backlog
Sprint 1 backlog
Effort-Hour Capacity
[7 empty] | Person | Days Available | Hours for Scrum Activity | Min Hours per Day | Max Hours per Day | Min Available Effort-Hours | Max Available Effort-Hours
[7 empty] | Quang Huy | 13 | 16 | 6 | 9 | 62 | 101
[7 empty] | Hoang Huy | 12 | 16 | 4 | 8 | 32 | 80
[7 empty] | Ngoc Thien | 9 | 16 | 3 | 5 | 11 | 29
[7 empty] | Dinh Hieu | 9 | 16 | 3 | 5 | 11 | 29
[7 empty] | SUM |  |  |  |  | 116 | 239
Sprint Backlog
| ID | User Story | Tasks Name | Sprint tasks | Person in Charge | Estimated effort (hours)
| PBI-3 | All staff must agree to Terms and Conditions before they can submit | Staff function | Design ERD, database | Nguyen Le Hoang Huy
|  |  |  | Back-End: Login Function | Huynh Quang Huy
|  |  |  | Back-End : Logout Function | Ngọc Thien
|  |  |  | Back-End: Register function | Huynh Quang Huy |  | Admin là Admin
|  |  |  | Design Register Page | Ngọc Thien |  | QA Codinator chính là maketing Cordinator
|  |  |  | Design Login Page | Dinh Hieu |  | Cordinator hay nói cách khác trong bài của long là giáo viên , tạo được nơi post idea, tạo deadline đồ đồ đó
|  |  |  | Design Home Page | Huynh Quang Huy |  | Role cuối là Staff nha
|  |  |  | Test completed function | Dinh Hieu
| PBI-2 | All staff (academic and support) have the opportunity to submit one or more ideas | Staff function | Design ERD, database | Nguyen Le Hoang Huy |  | Hãy tượng tượng nó giống mô hình CMS
|  |  |  | Back-End: Create one or more ideas | Nguyen Le Hoang Huy |  | QA cordinator theo video thì sẽ tạo phòng lớp , tên phòng lớp , tên khóa học đồ đó, còn đối với mình chỉ cần tạo phòng là dc
|  |  |  | Back-End: View one or more ideas | Huynh Quang Huy |  | Cordinator là kiểu như giáo viên, giáo viên sẽ tạo deadline hoặc là cái categories, là cái nơi sẽ có tiêu đề, nơi mà học sinh(staff) có thể vào đó và post bài idea lên
|  |  |  | Back-End: Edit one or more ideas | Huynh Quang Huy |  | Role guest bỏ qua
|  |  |  | Back-End: Delete one or more ideas | Ngọc Thien
|  |  |  | Design Uploading Ideas Page | Dinh Hieu
| PBI-15 | An administrator is needed to maintain any system data, e.g. closure dates for each academic year, staff details |  | Design ERD, database | Nguyen Le Hoang Huy
|  |  |  | Create Admin role | Huynh Quang Huy
|  |  |  | Create accounts | Ngoc Thien
|  |  |  | View accounts | Dinh Hieu
|  |  |  | Edit accounts | Nguyen Le Hoang Huy
|  |  |  | Delete accounts | Ngoc Thien
|  |  |  | Design Admin Page | Huynh Quang Huy
| PBI-13 | Lists of Ideas need to be paginated